## Plan Work
Milestone |  | Missions | Finish date | Status
Step | topic
Start planning |  |  | 17/12/2023 | V | Learning technologies
1 | Planning the Subscription DB structure | According the Project characterization document, and adding another fiels like member image, summary movie etc… | 17/12/2023 | V
| Learning technologies | Redux Toolkit with Redux Persist | 18-28/12/2023 | V | Milestone |  | Learning sources
|  | Web Socket (socket.io) | 18-28/12/2023 | V | Step | topic | Topic / Article | Link
|  | Recommendations with Collaborative Filtering methods | 18-28/12/2023 | V | 1 | Redux Toolkit with Redux Persist | Get rid of data consistency with the redux-persist | https://medium.com/@dharacharolap/get-rid-of-data-consistency-with-the-redux-persist-86559e96de32
|  | Advanced programming with React | 18-28/12/2023 | V |  |  | PersiPersist state with Redux Persist using Redux Toolkit in React | https://blog.logrocket.com/persist-state-redux-persist-redux-toolkit-react/
|  | React Context and useContext() Hook | 18-28/12/2023 | V | 2 | Web Socket (socket.io) | Building a chat app with Socket.io and React 🚀 | https://dev.to/novu/building-a-chat-app-with-socketio-and-react-2edj
|  | Theming with Sass | 18-28/12/2023 | V | 3 | Recommendations system | Using OpenAI API for recommendation systems | https://medium.com/muthoni-wanyoike/using-openai-api-for-recommendation-systems-6f7fc90c371e
| [screens & components] <=> [structure & design] | Planning the both structure and design of screens and components | 18-28/12/2023 | V |  |  | Predicting Likes: Inside A Simple Recommendation Engine’s Algorithms | https://www.toptal.com/algorithms/predicting-likes-inside-a-simple-recommendation-engine
Start programing |  |  | 28/12/2023 | V |  |  | collaborative-filter (npm i collaborative-filter) | https://www.npmjs.com/package/collaborative-filter
2 | Build Subscription WS | Build the subscription WS to work against Movies WS and Members WS, then deploy the data into mongoDB collections | 28-31/12/2023 | V |  |  | Building a Recommendation System with Node.js and MongoDB: A Step-by-Step Guide | https://voskan.host/2023/03/04/building-a-recommendation-system-with-node-js-and-mongodb/
3 | Tests Subscription WS | Performing the subscription WS tests with a postman | 31/12/23 | V | 4 | Advanced programming with React | How To Structure React Projects From Beginner To Advanced | https://blog.webdevsimplified.com/2022-07/react-folder-structure/
4 | Build Cinema WS | Build the cinema WS to work against users collection into mongoDB, users and permissions json files. And adding authentication with JWT | 1-4/1/2024 | V |  |  | What Are Pure Functions? | https://blog.webdevsimplified.com/2020-09/pure-functions/
5 | Tests Cinema WS | Performing the cinema WS tests with a postman | 2024-04-01 | V | 5 | React Context and useContext() Hook | A Guide to React Context and useContext() Hook | https://dmitripavlutin.com/react-context-and-usecontext/
6 | Build The Client (React) | Build the client with react, and connect to the cinema WS | 4-7/1/2024 |  | 6 | Theming with Sass | How to Create Powerful Themes Using SCSS | https://www.turing.com/kb/how-to-create-powerful-themes-using-scss
7 | Tests of the system | Perform advanced testing of the system by working with all data sources and testing the various modes | 2024-07-01 |  |  |  | Theming a React app with Sass modules: a step-by-step guide | https://medium.com/@thibaudbrault/theming-a-react-app-with-sass-modules-76aa0627297c
8 | First expansion of the system | Add dashboard screen for admin users (use web socket) | 8-9/1/2024 |  |  |  | Sass (Syntactically Awesome Style Sheets) | https://www.tutorialsteacher.com/sass
9 | Second expansion of the system | Add chat screen for messaging between the system users (use web socket) | 10-11/1/2024
10 | Third expansion of the system (optional in the futue) | Add recommendation movies of members Page - using Collaborative Filtering methods (by the cosine similarity algorithm) | 12-13/1/2024
11 | Optimization | Optimize the use of the system using a memorization module | 14/1/2024
12 | Last Tests | Perform advanced testing of the system by working with all data sources and testing the various modes | 15/1/2024
13 | Readme file | Filling out the Readme file | 16/1/2024
14
15
16
[5 empty] | gray | warning | success | error
[5 empty] | gray | orange | success | error
[5 empty] | #D2D2D2 | #F7BDA4 | #B5D5A7 | #FF9B9B
[5 empty] | #B3B6B9 | #EC9762 | #479D6E | #9D476C | thirdly | secondary | primary
[9 empty] | info | warning | secondary | primary
[9 empty] | #ABEDEF | #FFDD9C | #D4B1E9 | #B1CBE9 | light
main
[9 empty] | #ABEDEF | #9D9347 | #6D4789 | #3B75A9 | Dark
200
800
[10 empty] | light | #e3f2fd
[10 empty] | main | #2196f3
[10 empty] | Dark | #1e88e5
[10 empty] | 200 | #90caf9
[10 empty] | 800 | #1565c0

## Data Base Structure
Designing a MongoDB schemas |  |  | Designing a MongoDB schemas
| Subscriptions DB |  |  | Users DB
Collection | Document |  | Collection | Document
| Field (type) | Validation (rules) |  | Field (type) | Validation (rules)
Members | _id :ObjectId('64f3210ec5dfffce0b02dab0') | required, uniqe | users | _id :ObjectId('64f3210ec5dfffce0b02dab0') | required, uniqe
| name :{ type: String } | required |  | username :{ type: String } | required, uniqe
| email :{ type: String } | required, uniqe |  | password :{ type: String } | required
| city :{ type: String } | required
| image :{ type: String, url of image } | required
Designing a Json Files
Collection | Document |  | file | Document
| Field (type) | Validation (rules) |  | Field (type) | Validation (rules)
Movies | _id :ObjectId('64f3210ec5dfffce0b02dab0') | required, uniqe | users.json | _id :ObjectId('64f3210ec5dfffce0b02dab0') | required, uniqe (The _id that created in the data base)
| name :{ type: String } | required |  | firstName :{ type: String } | required
| genres :[ type: Array of Strings ] | required |  | lastName :{ type: String } | required
| image :{ type: String, url of image } | required |  | published :{ type: Date } | required
| type :{ type: String } | required |  | sessionTimeOut :{ type: Number } | required (the duration in minutes a user can work on the system once he logged in)
| language :{ type: String } | required |  | src :{ type: String, url of image } | required
| summary :{ type: String } | required
| premiered :{ type: Date } | required | file | Document
|  |  |  | Field (type) | Validation (rules)
Collection | Document |  | permissions.json | _id :ObjectId('64f3210ec5dfffce0b02dab0') | required, uniqe (The _id that created in the data base)
| Field (type) | Validation (rules) |  | permissions :[ type: Array of permissions] | required
Subscriptions | _id :ObjectId('64f3210ec5dfffce0b02dab0') | required, uniqe |  | { view subscriptions: boolean }, | required
| memberId :{ type: ObjectId } | required |  | { create subscriptions: boolean }, | required
| subscriptionMovies :[ type: Array of Json { movieId: ObjectId, date: Date.now() } ] | required |  | { update subscriptions: boolean }, | required
|  |  |  | { delete subscriptions: boolean }, | required
|  |  |  | { view movies: boolean }, | required
|  |  |  | { create movies: boolean }, | required
|  |  |  | { update movies: boolean }, | required
|  |  |  | { delete movies: boolean } | required

## Initial Data
Collection | Document
| Field (type) | Validation (rules)
users | _id :ObjectId('64f3210ec5dfffce0b02dab0') | required, uniqe
| username :{ type: String } | required, uniqe
| password :{ type: String } | required
file | Document
| Field (type) | Validation (rules)
users.json | _id :ObjectId('64f3210ec5dfffce0b02dab0') | required, uniqe (The _id that created in the data base)
| firstName :{ type: String } | required
| lastName :{ type: String } | required
| published :{ type: Date } | required
| sessionTimeOut :{ type: Number } | required (the duration in minutes a user can work on the system once he logged in)
| src :{ type: String, url of image } | required
file | Document
| Field (type) | Validation (rules)
permissions.json | _id :ObjectId('64f3210ec5dfffce0b02dab0') | required, uniqe (The _id that created in the data base)
| permissions :[ type: Array of permissions] | required
| { view subscriptions: boolean }, | required
| { create subscriptions: boolean }, | required
| { update subscriptions: boolean }, | required
| { delete subscriptions: boolean }, | required
| { view movies: boolean }, | required
| { create movies: boolean }, | required
| { update movies: boolean }, | required
| { delete movies: boolean } | required
"users": [
{
"_id": "ObjectId('64f3210ec5dfffce0b02dab0')",
"username": "DanaLevi",
"password": "123456"
}
]
"users": [
{
"_id": "ObjectId('64f3210ec5dfffce0b02dab0')",
"firstName": "Dana",
"lastName": "Levi",
"published": "123456",
"sessionTimeOut": "1440",
"src": "https://source.unsplash.com/collection/9948714?32",
}
]
"users": [
{
"_id": "ObjectId('64f3210ec5dfffce0b02dab0')",
"permissions": [
{ "viewSubscriptions": "true" },
{ "createSubscriptions": "true" },
{ "updateSubscriptions": "true" },
{ "deleteSubscriptions": "true" },
{ "viewMovies": "true" },
{ "createMovies": "true" },
{ "updateMovies": "true" },
{ "deleteMovies": "true" }
]
}
]

## App Structure
App Structure
main.jsx
App.jsx
MinimalLayout
MainLayout
router
LoginRoutes
MainRoutes
GuestGuard
AuthGuard
isLoggedIn
!isLoggedIn
Yes
Dashboard Page
Login Page
No

## Pages
Screen Design
Colors
Main (Dashboard)
|  |  |  | Sign In | Bachground |  | Borders
#15162f
#eeeeee
#e9ecec
#b1daff
#1976D2
Chat
Sign Up
Recommendations
|  | Jan | 40
|  | Feb | 30
|  | Mar | 35
|  | Apr | 25
|  | May | 14
|  | Jun | 30
|  | Jul | 32
|  | Aug | 39
|  | Sep | 45
|  | Oct | 60
|  | Nov | 55
|  | Dec | 24
Movies Model
Members Model
Users Model
8
Chat Page
Recommended Page
All Movies Page
All Members Page
Add Member Page
Add Movie Page
Sign In Page
Sign Up Page
Main Page (Dashboard)
Subscription Movie
Cinema Managment
Cinema Managment
Cinema Managment
Sign Up
Enter your credentials to continue
Sign Up
Already have an account?
Cinema Managment
Hi, Welcome Back
Enter your credentials to continue
Username:
____________
Password:
____________
Sign In
Don't have an account? Sign Up
Username:
____________
Password:
____________
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
Subscription
total subscribions
Number
Online Users
total number of active users
Number
Total Users
total number of users in the company
Number
Top movies subscribions
The Top members in ordering movies
New users
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
Chating panel
Users
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
Collapsible Table
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
Num Name Email City
1 Leanne Graham Sincere@april.biz Gwenborough
{ Under the Dome }
Scripted
Num Icon Name Genres Type Premiered
* Drama
* Science-Fiction
* Thriller
2011-09-22
1
All Movies
Add Movie
All Members
Add Member
* Avi Cohen, 22/12/2023
* Dana Levy, 20/12/2023
Subscriptions watched
Genres
Type
Language
* Drama
* Science-Fiction
* Thriller
Scripted
English
Under the Dome, [Premiered: 2011-09-22]
Edit
Delete
Under the Dome is the story of a small town that is suddenly and inexplicably sealed off from the rest of the world by an enormous transparent dome. The town's inhabitants must deal with surviving the post-apocalyptic conditions while searching for answers about the dome, where it came from and if and when it will go away
* Avi Cohen, 22/12/2023
* Dana Levy, 20/12/2023
Subscriptions watched
Genres
Type
Language
* Crime
* Action
* Science-Fiction
Scripted
English
Person of Interest, [Premiered: 2011-09-22]
Edit
Delete
You are being watched. The government has a secret system, a machine that spies on you every hour of every day. I know because I built it. I designed the Machine to detect acts of terror but it sees everything.
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
All Movies
Add Movie
Add Movie
_____________
_[array strings]_
Name:
Genres:
_____________
_____________
Image Url:
Premiered:
Save
Cancel
Edit Movie Page
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
All Movies
Add Movie
Edit Movie
_____________
_[array strings]_
Name:
Genres:
_____________
_____________
Image Url:
Premiered:
Update
Cancel
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
All Members
Add Member
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
All Members
Add Member
Edit Member Page
Add Member
_____________
_____________
Name:
Email:
_____________
City:
Save
Cancel
Edit Member
_____________
Name:
_____________
_____________
Email:
Premiered:
Update
Cancel
_____________
___________________
Type:
Language:
_____________
Summary
_____________
_____________
_____________
_____________
_____________
___________________
Type:
Language:
Summary
_____________
_____________
_____________
_____________
_____________
Subscription Drop Down
Users Managment Page
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
All Users
Add User
Add User Page
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
All Users
Add User
Edit User Page
Dashboard
icon
Movies
icon
Subscriptions
icon
User
Managment
icon
Chat
icon
Recommend
Movies
icon
Cinema Managment
Search
All Users
Add User
* Under the Dome, 22/12/2023
* Person of Interest, 20/12/2023
Movies watched
Email
City
avi@gmail.com
Tel Aviv
Avi Cohen
Edit
Delete
Subscribe to new movie
Add new movie
Choose Movie
Watched date
Subscribe
* Under the Dome, 22/12/2023
* Person of Interest, 20/12/2023
Movies watched
Email
City
dana@gmail.com
Haifa
Dana Livi
Edit
Delete
Subscribe to new movie
Add new movie
Choose Movie
Watched date
Subscribe
_____________
Image Url:
_____________
Image Url:
User Name
Session time out
avi@gmail.com
Tel Aviv
Edit
Delete
Email
Avi Cohen
Created Data
11/12/1998
Permissions
* View Subscriptions
* View Movies
* Edit Movies
* Update Movies
User Name
Session time out
dana@gmail.com
Haifa
Edit
Delete
Email
Dana Levi
Created Data
11/12/1990
Permissions
* View Subscriptions
* View Movies
* Edit Movies
* Update Movies
* Delete Movies
Add User
_____________
___________________
_____________
_____________
Save
Cancel
_____________
view subscriptions
Created User:
Permissions:
update subscriptions
delete subscriptions
view movies
create movies
update movies
First Name:
Last Name:
User Name:
Session Time Out:
create subscriptions
□
delete movies
□
□
□
□
□
□
□
√
√
Edit User
Update
Cancel
_____________
___________________
_____________
_____________
_____________
view subscriptions
Created User:
Permissions:
update subscriptions
delete subscriptions
view movies
create movies
update movies
First Name:
Last Name:
User Name:
Session Time Out:
create subscriptions
□
delete movies
□
□
□
□
□
□
□
√
√

## Dependencies
Dependencies

## process
Num | Tasks | Usages | File in my app | Details | Other Details / Links
1 | npm | Use axios |  | axios
2 | npm | Use redux toolkit & persist |  | react-redux @reduxjs/toolkit redux-persist
3 | npm | Use mui - material |  | @mui/material @mui/icons-material @mui/x-date-pickers @emotion/react @emotion/styled
4 | npm | Use router |  | react-router-dom
5 | npm | Use sass |  | sass
6 | npm | breaking hooks rules - defining rules inside this file | .eslintrc.cjs | npm install eslint-plugin-react-hooks --save-dev | // Your ESLint configuration
{
"plugins": [
// ...
"react-hooks"
],
"rules": {
// ...
"react-hooks/rules-of-hooks": "error", // Checks rules of Hooks
"react-hooks/exhaustive-deps": "warn" // Checks effect dependencies
}
}
| Declared useSelector and useDispatch in my RootState [app] | ready to be used everywhere in your application | store.js |  | https://stackoverflow.com/questions/71408731/dispatch-in-pure-js-code-using-react-with-redux-toolkit
| Destructure from store the dispatch function as a pure JavaScript module | able us to use it outside of React components | store.js | On a runtime level, they are 100% equal. The difference is that one is untyped so the state variable is unknown and needs to be manually typed by you on every single call of useSelector - and you can pass in everything wrong there without causing an error. useAppSelector on the other hand gets declared with your RootState in one place and after that it's typesafe, ready to be used everywhere in your application | https://stackoverflow.com/questions/73352741/difference-between-useselector-and-useappselector